## 2026 Garden Plan
2026 Garden Plan — Jeanius Kitchen Garden
Zone 4b/5a ¦ Last Frost: ~May 15 ¦ First Frost: ~Oct 1 ¦ Growing Season: ~138 days
Plant Name | Variety | Source | Seed Cost | Started From | Quantity | Location / Plot | Start Indoors — Target | Start Indoors — Actual | Transplant — Target | Transplant — Actual | Direct Sow — Target | Direct Sow — Actual | Days to Maturity | Harvest — Target | Harvest — Actual | Spacing | Companion Plants | Destination | Notes / Lessons
Asparagus | TBD (crowns) |  |  | Crowns | TBD | TBD |  |  |  |  | Apr-May (plant crowns) |  | 2-3 years to full harvest
Basil | Genovese | Burpee | 5.95 | Seed | 4 | Main Garden | Apr 3 |  | May 22 |  |  |  | 60-70 | [5 empty] | Burpee order 3/2/26 — 250 organic seeds, $5.95
Bush Beans | Blue Lake | Burpee | 4.95 | Seed (direct sow) | 10 ft row | Phil's Plot |  |  |  |  | May 18 |  | 50-60 | [5 empty] | Burpee order 3/2/26 — 2 oz, $4.95
Bush Beans | Blue Lake (2nd sowing) |  |  | Seed (direct sow) | 10 ft row | Phil's Plot |  |  |  |  | Jun 8 |  | 50-60
Cilantro | Calypso | Burpee | 5.95 | Seed (direct sow) | 2 ft row | Main Garden |  |  |  |  | Apr 25 |  | 50-55 | [5 empty] | Burpee order 3/2/26 — 200 seeds, $5.95
Cilantro | Calypso (2nd sowing) |  |  | Seed (direct sow) | 2 ft row | Main Garden |  |  |  |  | May 15 |  | 50-55
Cilantro | Calypso (3rd sowing) |  |  | Seed (direct sow) | 2 ft row | Main Garden |  |  |  |  | Aug 1 |  | 50-55
Cucumber | Fresh Pickles | Burpee | 6.95 | Seed (direct sow) | 4 | Phil's Plot |  |  |  |  | May 20 |  | 50-55 | [5 empty] | Burpee order 3/2/26 — 20 seeds, $6.95
Cucumber | Slicing (Marketmore) |  |  | Seed (direct sow) | 2 | Phil's Plot |  |  |  |  | May 20 |  | 55-65
Daikon Radish | Long | Burpee | 4.95 | Seed (direct sow) |  | TBD | [6 empty] | 60-70 | [5 empty] | Burpee order 3/2/26 — 300 seeds, $4.95
Dill | Bouquet |  |  | Seed (direct sow) | 3 | Main Garden |  |  |  |  | May 1 |  | 40-60
Hibiscus | Honeymoon Red F1 | Burpee | 6.95 | Seed | 6 | TBD | TBD | Mar 14 (paper towel/bag method) | May 22 |  |  |  | — | [5 empty] | Burpee order 3/2/26 — 5 seeds, $6.95
Lettuce | Mesclun Mix |  |  | Seed (direct sow) | 4 ft row | Main Garden |  |  |  |  | Apr 20 |  | 30-45
Lettuce | Mesclun Mix (2nd) |  |  | Seed (direct sow) | 4 ft row | Main Garden |  |  |  |  | May 10 |  | 30-45
Lettuce | Mesclun Mix (3rd) |  |  | Seed (direct sow) | 4 ft row | Main Garden |  |  |  |  | Aug 1 |  | 30-45
Marigold | French Dwarf | 2025 leftover seeds | 0 | Seed (winter sow) | 3 milk jugs | Main Garden & Phil's Plot |  |  | May 15 |  | Winter sow |  | — | [5 empty] | Winter sow in milk jugs, transplant after last frost
Mushroom | Oyster | Field & Forest Products | 20 | Spore plugs | 100 plugs / ~2 logs | Shade/woods — logs (TBD) |  |  |  |  | Apr-May (inoculate logs) |  | 6-12 months | [5 empty] | Field & Forest Oyster Plug Spawn Starter Kit (Tiny) — 100 plugs, drill bit, wax, tags, instructions
Mushroom | Shiitake | Field & Forest Products | 25 | Sawdust spawn | 5 lb bag / ~5 logs | Shade/woods — logs (TBD) |  |  |  |  | Apr-May (inoculate logs) |  | 6-12 months | [5 empty] | Field & Forest Shiitake WR46 Sawdust Spawn — 5 lb bag
Onion | Yellow (sets) |  |  | Sets | 36 | Main Garden |  |  |  |  | Apr 20 |  | 90-120 | [5 empty] | Need to buy sets
Oregano | Greek |  |  | Seed | 2 | Main Garden | Mar 25 |  | May 22 |  |  |  | 70-90
Pepper | Bell (mixed colors) | Uncle's starts | 0 | Transplant | 6 | Phil's Plot | Mar 13 | Uncle's starts | May 22 |  |  |  | 70-80
Pepper | Candlelight | High Mowing Organic Seeds | 0 | Seed | 9 | Phil's Plot | Mar 3 | Mar 3 | May 22 |  |  |  | 60-70
Pepper | Cayenne |  |  | Seed | 3 | Phil's Plot | Mar 13 | Not planting 2026 | May 22 |  |  |  | 70-80
Pepper | Orange Habanero | High Mowing Organic Seeds | 0 | Seed | 9 | Phil's Plot | Mar 3 | Mar 3 | May 22 |  |  |  | 90-100
Pepper | Hungarian Hot Wax | High Mowing Organic Seeds | 0 | Seed | 11 | Phil's Plot | Mar 13 | Mar 3 | May 22 |  |  |  | 60-70
Pepper | Jalapeño |  |  | Seed | 4 | Phil's Plot | Mar 13 |  | May 22 |  |  |  | 65-75
Pepper | Poblano |  |  | Seed | 3 | Phil's Plot | Mar 13 |  | May 22 |  |  |  | 65-75
Potato | Rocky Mountain Russet / Red Pontiac |  |  | Seed potatoes | TBD | Potato boxes (build) |  |  |  |  | Apr-May |  | 70-120
Rhubarb | — |  |  | Established | 4 | Main Garden | [6 empty] | — | [5 empty] | 4 established plants by Main Garden
Rosemary | — |  |  | Transplant (buy) | 1 | Container |  |  | Buy transplant |  |  |  | —
Snap Peas | Sugar Snap | Burpee | 10.9 | Seed (direct sow) | 10 ft row | Main Garden |  |  |  |  | Apr 15 |  | 55-65 | [5 empty] | Burpee order 3/2/26 — 600 seeds (2 packs), $10.90
Snap Peas | Sugar Snap (2nd sowing) |  |  | Seed (direct sow) | 10 ft row | Main Garden |  |  |  |  | Apr 30 |  | 55-65
Thyme | Common |  |  | Seed | 2 | Main Garden | Mar 25 |  | May 22 |  |  |  | 70-90
Tomato | Beefsteak | Uncle's starts | 0 | Seed | 3 | Phil's Plot | Mar 20 | Uncle Bill's starts (Mar 7) | May 20 |  |  |  | 75-85
Tomato | Cherry (Sungold) | Burpee | 6.45 | Seed | 3 | Phil's Plot | Mar 20 | Mar 14 (paper towel/bag method) | May 20 |  |  |  | 60-65 | [5 empty] | Burpee order 3/2/26 — 30 seeds, $6.45
Tomato | Roma |  |  | Seed | 6 | Phil's Plot | Mar 20 |  | May 20 |  |  |  | 75-80
Tomato | San Marzano | 2025 leftover seeds | 0 | Seed | 6 | Phil's Plot | Mar 20 | Mar 3 | May 20 |  |  |  | 78-85
Tomato | SuperSauce | Burpee | 6.95 | Seed |  | Phil's Plot | TBD | Mar 14 (paper towel/bag method) | May 20 |  |  |  | 70-80 | [5 empty] | Burpee order 3/2/26 — 25 seeds, $6.95
Zucchini | Black Beauty |  |  | Seed (direct sow) | 3 | Phil's Plot |  |  |  |  | May 20 |  | 45-55

## Harvest Log
2026 Harvest Log
Track what you pick, how much, and what you do with it. This data feeds next year's plan.
Date | Plant | Variety | Quantity / Weight | Destination | Quality Notes | Preservation Notes
Jul 15 | Tomato | Cherry (Sungold) | 2 lbs | Fresh eating | Perfect ripeness
Aug 1 | Tomato | Roma | 15 lbs | Canning (salsa) | Firm, good color | Batch 1 — 7 pints salsa
Aug 5 | Pepper | Bell (red) | 8 peppers | Freezing (diced) | Full size, thick walls | Diced and frozen in 1-cup bags

## Season Calendar
2026 Season Calendar — Wisconsin Zone 4b/5a
Key dates and tasks by month. Adjust based on actual weather conditions.
Month | Key Dates | Start Indoors | Direct Sow | Transplant | Harvest | Preservation Tasks | Notes
January |  | Order seeds Review last year's notes |  |  |  |  | Planning phase — set preservation goals
February |  | Order seeds if not done Clean seed trays |  |  |  |  | Finalize garden layout and quantities
March | Mar 3: Started peppers + San Marzano Mar 13: Start remaining peppers (planned) Mar 20: Start remaining tomatoes (planned) | Peppers — Candlelight, Habanero, Hungarian Hot Wax (Mar 3) San Marzano tomatoes (Mar 3) Remaining peppers (Mar 13) Remaining tomatoes (Mar 20) |  |  |  |  | Started early from 2025 leftover seeds on 3/3. Burpee order placed 3/2 — seeds shipped.
April | Apr 3: Start basil Apr 20: Cool crops out | Basil (Apr 3) | Lettuce, radish, cilantro (Apr 20-25) Onion sets (Apr 20) |  |  |  | Watch weather — cool crops tolerate light frost
May | May 1: Dill direct sow ~May 15: LAST FROST May 18-22: Transplant |  | Beans (May 18) Cucumbers (May 20) Zucchini (May 20) Cilantro 2nd (May 15) | Tomatoes (May 20) Peppers (May 22) Basil (May 22) Marigolds (May 15) | Radishes Lettuce (early) |  | Harden off transplants for 7-10 days before moving outside
June |  |  | Beans 2nd sowing (Jun 8) |  | Lettuce, radishes, herbs begin |  | Succession sow lettuce and radishes
July |  |  |  |  | Beans, cucumbers, zucchini, cherry tomatoes begin | Start freezing zucchini, herbs | Peak growth — water deeply, fertilize weekly
August | Aug 1: Fall lettuce Aug 1: Fall cilantro |  | Lettuce 3rd (Aug 1) Cilantro 3rd (Aug 1) |  | PEAK HARVEST Tomatoes, peppers, beans, cucumbers | Canning season! Salsa, sauce, pickles, dilled beans | Busiest month. Schedule preservation days.
September |  |  |  |  | Tomatoes, peppers (late), beans (late), fall lettuce | Continue canning Freeze peppers Dehydrate herbs | Watch for first frost warnings
October | ~Oct 1: FIRST FROST |  |  |  | Pull remaining crops before frost | Final preservation Cure onions Process green tomatoes | Cover sensitive crops if frost comes early
November | [5 empty] | Inventory preserved food. Plan next year. | Season wrap-up. Write lessons learned!

## Blank Template
Garden Planning Template — Customize for Your Zone
Fill in your zone, frost dates, and crops. Delete the example rows and add your own.
Your Zone: _____ ¦ Last Frost: _____ ¦ First Frost: _____ ¦ Growing Season: _____ days
Plant Name | Variety | Source | Seed Cost | Started From | Quantity | Location / Plot | Start Indoors — Target | Start Indoors — Actual | Transplant — Target | Transplant — Actual | Direct Sow — Target | Direct Sow — Actual | Days to Maturity | Harvest — Target | Harvest — Actual | Spacing | Companion Plants | Destination | Notes / Lessons

## Risk Register
Garden Risk Register — 2026
Identify risks before they become problems. Review monthly during growing season.
Risk ID | Risk Description | Category | Probability | Impact | Risk Score | Mitigation Strategy | Trigger / Early Warning | Owner | Status | Date Identified | Notes
R-01 | Late spring frost kills transplants | Weather | Medium | High | High | Monitor forecasts. Keep row covers ready. Don't transplant warm crops before May 20. | Frost advisory before May 20 | Jean | Open | Feb 2026 | Lost peppers to late frost in 2024. Now wait a week past average last frost.
R-02 | Black walnut juglone affects sensitive crops | Site | High | Medium | High | Plant tomatoes and peppers in Phil's Plot only. Main Garden for tolerant crops. | Wilting/yellowing near walnut tree | Jean | Mitigated | 2023 | Identified after 2 seasons of poor performance in Main Garden east end.
R-03 | Rabbit/deer damage to garden | Pests | High | Medium | High | Fencing around plots. Marigolds as deterrent. Monitor for gaps in barrier. | Nibbled leaves, tracks, droppings | Jean | Open | Feb 2026 | Rabbits are persistent. The lettuce buffet comment is real.
R-04 | Seeds fail to germinate | Seeds | Low | Medium | Medium | Start extra seeds (20% buffer). Test germination of older seeds before planting season. | No sprouts 7-10 days past expected germination | Jean | Open | Feb 2026 | 2025 was first year of pepper success from seed. Tomatoes from seed still inconsistent.
R-05 | Drought / insufficient watering | Weather | Medium | High | High | Mulch beds. Water deeply 2-3x/week. Container plants daily. Set phone reminders. | Wilting, dry soil 2" deep | Jean | Open | Feb 2026 | Uncle's advice: water frequently if it doesn't rain. Containers need extra.
R-06 | Overcrowding — rows planted too close | Planning | High | Medium | High | Follow spacing in spreadsheet. Mark actual distances. SPACE THEM OUT. | Plants touching before midsummer | Jean | Open | Feb 2026 | Every year I plant rows too close. Noted in spreadsheet. Still do it. THIS YEAR: measure.
R-07 | Blight or disease in tomatoes | Disease | Medium | High | High | Rotate tomato location yearly. Remove affected plants immediately. Don't overhead water. | Brown spots on lower leaves, wilting | Jean | Open | Feb 2026 | Rotate between Phil's Plot sections each year.
R-08 | Not enough tomatoes for canning goals | Yield | Medium | High | High | Plant 18+ tomato plants. Include sauce varieties (San Marzano, SuperSauce). | Fewer than expected fruit set by July | Jean | Open | Feb 2026 | Never feel like there are enough. Added SuperSauce for 2026.
R-09 | Early fall frost ends season prematurely | Weather | Medium | Medium | Medium | Monitor forecasts in September. Harvest green tomatoes for ripening indoors. Cover sensitive crops. | Frost advisory before Oct 1 | Jean | Open | Feb 2026 | Have a harvest-everything plan ready for first frost warning.
R-10 | Burpee/seed order arrives late | Supply | Low | Medium | Low | Order early (Feb). Track shipping. Have backup seed source identified. | No shipping confirmation 2 weeks after order | Jean | Closed | Feb 2026 | 2026 Burpee order placed 3/2, shipped promptly.

## Stakeholder Register
Stakeholder Register & Preservation Orders — 2026
Who wants what, and how much? This drives how much to plant. Fill in quantities each January.
|  |  | CANNING | [8 empty] | FREEZING |  |  |  |  | DEHYDRATING | [5 empty] | FRESH
Stakeholder | Role | Notes | Salsa (pints) | Pasta Sauce (quarts) | Tomato Paste (half-pints) | Pickles (pints) | Straw-Rhub Jam (hp) | Blueberry Jam (hp) | Blueberry Pie Filling (qt) | Canned Peaches (qt) | Applesauce (quarts) | Diced Peppers (bags) | Frozen Tomatoes (bags) | Frozen Berries (bags) | Frozen Corn (bags) | Frozen Beans (bags) | Dried Basil | Dried Oregano | Dried Rosemary | Dried Cilantro | Dried Dill | Tomato Powder | Fresh Eating (weekly lbs) | Give Away (priority)
Jean (household) | Garden owner / planner | Primary consumer. Drives all planting decisions. | 12 | 8 | 6 | 8 | 6 | 6 | 4 | 7 | 6 | 10 | 6 | 4 |  | 4 | 2 | 2 | 1 | 1 | 1 | 2 | 5-10
Family (extended) | Holiday / gathering recipients | Christmas gifts, family gatherings. Jams and salsa are most popular. | 4 |  |  |  | 4 | 4
Friends & neighbors | Surplus recipients | Share during peak harvest. Peppers and tomatoes most common. | 2 |  |  | 2 | 2 | 2 |  |  |  | 4 | [10 empty] | varies | Yes
Phil | Plot partner | Shares Phil's Plot. Gets share of harvest from shared space. | [20 empty] | ?
Uncle | Mentor / supplier | Provides bell pepper starts. Gets surplus in return. | [20 empty] | ?
Vince | Son
Angie | Daughter
Scott | Son
TOTAL NEEDED |  | Sum drives garden plan →
hp = half-pint jars ¦ qt = quart jars ¦ bags = quart freezer bags
Fill in quantities each January. Totals drive how many plants to grow.
? = need to ask ¦ blank = not applicable for this stakeholder

## Issues & Changes
Issues & Change Log — 2026
Track problems as they happen and document plan changes so you know WHY things shifted.
ISSUES LOG
Issue ID | Date Identified | Description | Category | Impact | Action Taken | Date Resolved | Status | Lessons for Next Year
I-01 | Jun 2024 | Late frost killed pepper transplants | Weather | Lost 6 pepper plants | Replanted from uncle's starts. Pushed transplant date back 1 week for 2025+. | Jun 2024 | Closed | Don't transplant warm crops before May 20, regardless of forecast optimism.
I-02 | Jul 2024 | Tomatoes stunted in Main Garden east end | Site | 50% yield loss in affected area | Researched — identified black walnut juglone. Moved sensitive crops to Phil's Plot. | 2025 season | Closed | Map juglone zone. Only plant tolerant crops in Main Garden.
I-03 | Aug 2025 | Rows planted too close — overcrowding | Planning | Reduced airflow, harder to harvest | Noted in spreadsheet. Plan to measure and mark spacing in 2026. | Ongoing | Open | MEASURE spacing. Don't eyeball it. You say this every year.
CHANGE LOG
Change ID | Date | Original Plan | Change Made | Reason | Impact on Schedule | Impact on Yield | Approved By | Notes
C-01 | Mar 3 | Start peppers Mar 13 | Started peppers Mar 3 (10 days early) | Had 2025 leftover seeds — wanted to use them before viability dropped | Earlier start = earlier harvest | Potentially more plants to choose from | Jean | Hungarian Hot Wax (11), Candlelight (9), Habanero (9)
C-02 | Mar 2 | No SuperSauce tomato | Added SuperSauce variety (Burpee order) | Want a dedicated large sauce tomato for canning | Fits existing schedule | More sauce tomatoes for canning | Jean | NEW for 2026. 25 seeds ordered.
C-03 | Mar 2 | Santo cilantro | Switched to Calypso cilantro | Calypso is slower to bolt — better for Wisconsin heat | No change | Potentially longer cilantro harvest | Jean | Burpee order — 200 seeds
C-04 | Feb 2026 | Bell peppers from seed | Getting transplants from uncle instead | Uncle has reliable starts. Focus seed-starting effort on other varieties. | No indoor start needed for bells | Same — uncle's starts are strong | Jean | Frees up grow light space for tomatoes

## Lessons Learned
Lessons Learned — Garden Seasons 2022–2025
What worked, what didn't, and what to do differently. Review every January before planning.
Year | Category | What Happened | What Worked | What Didn't Work | Action for Next Year | Status
2023 | Site | Discovered black walnut juglone affecting Main Garden | Moving sensitive crops to Phil's Plot solved the problem | Lost 2 seasons of tomato/pepper yield figuring this out | Map juglone zone permanently. Only tolerant crops in Main Garden. | Implemented
2024 | Weather | Late frost killed pepper transplants in early June | Uncle had backup starts — recovered most of the loss | Transplanted too early based on optimistic forecast | Don't transplant warm crops before May 20. Period. | Implemented
2024 | Planning | Rows too close together — overcrowding by midsummer | Plants grew fine individually | Airflow reduced, harder to harvest, more disease pressure | MEASURE spacing with a tape measure. Stop eyeballing it. | In Progress
2025 | Seeds | First year of pepper success from seed | Grow lights on a table in basement worked for peppers | Tomatoes from seed still inconsistent — leggy, poor survival rate | 2026: upgrading to grow tent with wire shelving + LED lights | In Progress
2025 | Preservation | Diced and froze so many peppers the freezer is packed | Having peppers in freezer year-round is a huge win | Could have planned freezer space better — ran out of room | Plan freezer inventory before harvest season. Give away more earlier. | Planned
2025 | Seeds | Winter sowed marigolds in milk jugs — great success | Easy, low-maintenance, excellent germination | Nothing — worked perfectly | Continue winter sowing marigolds. Try other flowers too. | Implemented
2025 | Growing | Uncle's advice: fertilize at planting, weekly feeding, frequent watering | Plants were healthier and more productive than previous years | Container plants still struggled — needed even more water/feeding | Weekly fertilizer schedule. Daily watering for containers. | Implemented
2025 | Harvest | Never feel like there are enough tomatoes for canning | 18 plants produced several batches of canned goods | Still not enough for all planned salsa, sauce, and fresh eating | 18+ plants again. Added SuperSauce variety for 2026. Plant more. | Planned
2025 | Preservation | Dried tomato skins into tomato powder — zero waste from canning | Great flavor booster. Easy to make. Uses what would be trash. | Nothing — pure win | Continue. Blog post about tomato powder coming. | Implemented
2022-25 | General | Moved from Seattle to Wisconsin — different climate, different approach | 4 seasons of data now. Know what works in Zone 4b/5a. | Generic gardening advice doesn't account for local conditions | Trust the spreadsheet. Trust site-specific observations over books. | Ongoing